## Sheet1
RISK | Risk Rating & Responsibilty |  |  | MEASURES ALREADY IN PLACE | PROPOSED MEASURES | RESPONSE
| Risk | Impact | Responsibilty
Database can be attacked via SQL Injection and could lead to a breach of user data including email's and password | Low | Medium | Harpreet Jhita
GCP server shuts down. As GCP is currently being used on a free trial/credit, the server will only run while the account is credited. Should the account run out of credit, the service will no longer work | Low | High | Harpreet Jhita